## Project plan Example
| Revision number | 4
|  |  | MONTH | Month 1 |  |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  |  | Month 11 |  |  |  | Month 12 |  |  |  | Month 13 |  |  |  |  | Month 14 |  |  |  | Month 15 |  |  |  | Month 16 |  |  |  |  | Month 17 |  |  |  | Month 18 |  |  |  | Month 19 |  |  |  |  | Month 20 |  |  |  | Month 21 |  |  |  | Month 22 |  |  |  |  | Month 23 |  |  |  | Month 24
STEP | ACTIVITY | LEAD PERSON | WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
1 | Develop the Vision
1.1 | Outline project vision and objectives
1.2 | Discuss and refine vision and objectives with all stakeholders
1.3 | Stakeholder agreement of vision and objctives
2 | Seek Advice
2.1 | Identify previous relevant projects
2.2 | Consult with groups who have undertaken these projects
3 | Communicate
3.1 | Plan community communication process for project
3.2 | Ongoing project communication (see below - update based on specific communication plan)
3.2.1 | Committee planning/progress meetings
3.2.2 | Questionnaire to community to test support for plans
3.2.3 | Open community meeting to discuss plans
3.2.4 | Disseminate draft and agreed project plan to community
3.2.5 | Compile evidence on community support for funders
3.2.6 | Provide progress updates to community
3.2.7 | Open day to celebrate project completion
3.2.8 | Periodic feedback on energy performance | [105 empty] | → | Ongoing - potentially monthly via website | Ongoing - potentially monthly via website
4 | Find a Site
4.1 | Identify potential sites for development
4.1 | Assess potential sites using steps in guidance
4.1 | Select site(s) for next steps
5 | Initial Scoping
5.1 | Utilise tools to provide initial esimates of energy and financial yield
5.2 | Carry out break point 1 (BP1) viability assessment
BP1 | IS THERE A REASON TO DEVELOP?
6 | Establish An Entity
6.1 | Set up activities
6.2 | Legal entity established
7 | Secure Initial Funds
7.1 | Source initial funding (apply for a CARES grant)
7.2 | Initial funding secured
8 | Pre-Feasibility Study
8.1 | Commission initial scoping study for potential sites
8.2 | Scoping study completed
9 | Financial Viability Check
9.1 | Use tools to assess and compare financial benefits
9.2 | Consider other key constraints identified
9.3 | Completed financial viability check
BP2 | DOES THE PROJECT HAVE POTENTIAL?
10 | Secure the Site
10.1 | Negotiate legal Exclusivity Agreement
10.2 | Agree and sign Exclusivity Agreement
11 | Full Feasibility Study
11.1 | Commission technical feasibility study
11.2 | Undertake scoping consultation with stakeholders (local community)
11.3 | Complete full feasibility study
12 | Confirm Grid Availability
12.1 | Ensure up-to-date grid information
13 | Pre-Planning Consultation
12.1 | Discussion with planning authority
14 | Neighbour Notification
14.1 | Contact residents within 1k of site
14.2 | Receive feedback from residents
BP3 | CAN THE CHALLENGES BE OVERCOME?
15 | Fix the Project Size
15.1 | Final agreement of all stakeholders on size of project to be taken forward
16 | Financial Viability Check
16.1 | Carry out further financial modelling
17 | Secure Pre-Planning funds
17.1 | Discussion and agreement on finance considerations
17.2 | Identification of suitable funding sources
17.3 | Application(s) for funding
17.4 | Receive funding
18 | Planning Application
18.1 | Apply for planning permission
18.2 | Approval of planning application
19 | Water Abstraction Licence Application
19.1 | Apply for water abstraction licence
19.2 | Granting of water abstraction licence
20 | Grid Application
20.1 | Make grid application
20.1 | Approval of grid application
21 | Identify Funding Sources
21.1 | Discussion and agreement on finance considerations
21.2 | Identification of suitable funding sources
21.3 | Application(s) for funding
21.4 | Receive funding
22 | Develop Full Financial Model
22.1 | Obtain quotes for all elements of work
22.2 | Finalise costs
22.3 | Use tools to complete financial appraisal and full business plan
BP4 | CONFIRM CONSENTS, GRID AND FINANCIAL VIABILITY
23 | Identify and Contact Suppliers
23.1 | Identify appropriate suppliers / develop tender documentation
23.2 | Carry out competitive tendering process
23.3 | Evaluate tenders
23.4 | Turbine supply contract signing and deposit
23.5 | O&M contract signing
23.6 | Civil works contractor appointment
23.7 | Electrical contractors appointment
23.8 | Leases signing date
23.9 | PPA signing date
24 | Secure Bridge Funds
24.1 | Funding programme/timetable, with cash flow
24.2 | Identification of suitable funding sources
24.3 | Application(s) for funding
24.4 | Receive funding
25 | FIT Pre-Accreditation
25.1 | Application for FIT pre-accreditation
26 | Financial Close
26.1 | Consider whether project can reach financial close (BP3)
26.2 | Due Diligence
26.3 | Secure finance through chosen route
BP4 | CAN THE PROJECT BE FUNDED?
27 | Repay Other Funds
27.1 | Repay debts where applicable
28 | Construction
28.1 | Construction CDM notification
28.2 | Civil contractors works
28.3 | Electrical contractors works
28.4 | Turbine installation schedule
29 | Community Benefit
29.1 | Enter into agreements with appropriate parties
30 | Operation | [105 empty] | → | Up to 25 years
30.1 | Turbine testing and commissioning
30.2 | All operation and maintenance activitites
30.3 | Decommissioning activities (at end of project lifetime)
31 | Decommissioning
31.1 | Decommissioning or refurbishment date | [106 empty] | End of project life →
Contract Payment Schedules
17 | Turbine
17.1 | Deposit
17.2 | Delivery
17.3 | Commisioning
18 | Grid Connection
18.1 | Contract
18.2 | Connection
18.3 | Final payment
19 | Construction
19.1 | Contract
19.2 | Project management
19.3 | Final payment