an suidhe Windfarm

# Repowering potential - community ownership

A summary of the An Suidhe Windfarm Repowering Feasibility Report

This summary report has been prepared by Carbon Trust on behalf of Energy Saving Trust to provide initial information on potential wind farm repowering opportunities on land managed by Forestry and Land Scotland.  This does not constitute a full feasibility study, technical design, financial appraisal or investment advice. No reliance whatsoever should be placed on the information contained within it.  Energy Saving Trust, Carbon Trust, Local Energy Scotland and associated parties do not give any warranty or undertaking or make any representation (in each case whether express or implied) regarding the accuracy, sufficiency or completeness of such information.

June 2026

# Introduction:

Repowering involves replacing older turbines with newer equipment so the site can continue generating electricity beyond the life of the current scheme. As part of the information available to communities considering repowering on Forestry and Land Scotland (FLS) sites, Local Energy Scotland has prepared early-stage feasibility studies. These are available on request via info@localenergy.scot.  This summary is intended to provide a high-level overview of the key messages from the full An Suidhe Windfarm Repowering Feasibility Report. It is based on very early-stage analysis and does not replace the full report. Rather, it is designed to help a community energy group quickly understand the potential opportunity, the main constraints, and the further work that would be required before making an informed decision about whether to pursue community ownership and submit a Community Asset Transfer note of interest (a formal request for community ownership or control of a public asset).

## The repowering opportunity in brief:

An Suidhe is an existing wind farm on Forestry and Land Scotland land in Argyll and Bute. The current wind farm has 23 turbines with a total installed capacity of 19.3 MW, and the present lease, held by RWE Renewables, expires in December 2033. The Feasibility Report was prepared to help community organisations understand whether repowering the site could be a realistic future opportunity under the Scottish Government’s wider approach to supporting community benefit and community participation in renewable energy projects.

For community groups, a repowered site could offer a long-term local asset, a stronger role in decision-making, and the potential to retain more economic value in the area. There are, however, challenges. The full report is still an early-stage assessment, with the requirement for substantial technical, commercial, environmental and legal work before a project could proceed.

Further work will be required to test site feasibility, but the report sets out three repowering options:-

- New turbines within the current grid connection capacity (18.9 MW),

- Refurbished turbines maintaining the current layout and grid connection capacity (19.3 MW), and

- New, larger turbines with a higher grid connection capacity (34.5 MW).

Initial, high-level financial modelling (at an early feasibility stage) suggests the following indicative results:

|  | 18.9 MW (21 new turbines) | 19.3 MW (23 refurbished turbines) | 34.5 MW (10 new turbines) |
| --- | --- | --- | --- |
| Total project costs (development plus capital) (no finance costs)​ | £36.9m​ | £33.2m | £67.3m |
| Payback period​ | 9.5 years​ | 12 years | 9 years |
| NPV (Net Present Value) (£) 3.5% discount rate (nominal) (using prices at the time, without adjusting for future inflation)​ | £32.1m | £9.5m | £69.4m |
| Project IRR (Internal Rate of Return) (nominal) (the estimated percentage return the project could generate, using current prices)​ | 10.20%​ | 6.35% | 11.25% |
| Cost per kW (£/kW) | £2,086 | £1,797 | £2,086 |

The actual economics could change significantly once development costs, financing terms, tax treatment, supply chain pricing, grid costs and contract arrangements are better understood.

Option 1 is more closely aligned with local planning guidance and is intended to reduce additional impacts on the site, especially in relation to peatland, landscape sensitivity and access. This option is likely to be the least problematic in terms of securing planning permission and maintaining a grid connection, whilst benefitting from the reliability and performance of new turbines compared with using refurbished turbines.

Option 3 is the most ambitious and shows the highest IRR and shortest payback period. It is, however, less aligned with current planning guidance and could face serious grid and consent challenges.

## Key challenges in pursuing the opportunity:

One of the most significant risks is planning. The site sits within a sensitive landscape and is surrounded by other existing and proposed renewable energy developments, so cumulative visual impact (the combined effect of several developments on how the landscape looks) is likely to be an issue. There is extensive peatland across the site, which matters both environmentally and for development design. Existing planning conditions, the changing policy context since the original wind farm was built, and the need to protect habitats, landscape character (the distinct appearance and features of an area) and local amenity, all indicate a future planning process would be detailed, evidence-heavy and potentially costly.

Commercial and delivery risks are also important. Third-party agreements (agreements with other organisations or landowners) are likely to present a challenge, especially grid arrangements and any agreements that may currently sit with the existing operator. Even where the site looks feasible in principle, a community organisation would still need to secure the necessary development rights, negotiate with key land and infrastructure parties, and confirm whether an existing grid connection could be retained or transferred. Without clarity on those points, a project could become delayed, more expensive, or impossible to progress on viable terms.

## What this means for a community energy group:

This is a substantial opportunity for community ownership, but also a substantial development project. While the site could deliver long-term local benefit, communities should recognise the scale, cost and complexity involved. CARES funding can help communities take the next step by supporting the further feasibility work needed to understand whether the opportunity is viable in practice if the community has appetite to investigate this.

The An Suidhe Windfarm Repowering Feasibility Report should be seen as a decision-support document rather than a final recommendation to proceed. It will help local organisations understand both the scale of the opportunity and the scale of the challenge. The report indicates there may be a credible pathway to community involvement in a repowered An Suidhe project, particularly if a realistic, planning policy-aligned scheme is pursued. It also shows a successful project would require building partnerships, securing specialist advice, and being prepared for a long development process.

In practical terms, a community group considering this opportunity would need to focus on their capability and readiness. This includes understanding governance, access to finance, procurement of specialist advisers, and the ability to engage constructively with Forestry and Land Scotland, network operators, planners, funders and local stakeholders.